## Project Chart
Project Chart
Project Name | Atlascan
Project Description | •The project involves the development of a robust cloud-native application that integrates OCR technology to automate the extraction of crucial information from identification documents. •The application should be capable of handling uploaded documents and camera feed. •The extracted data, specifically the ID number should be accurately transferred to a web form for a more streamlined and error-free user experience.
Project Manager - Scrum Master | ELBOUZIDI HAMZA
Business Case | •Inspired by the Filling payment card scanner tools used to fill out forms with data fast and easy. •Cloud-Native Application: Develop a cloud-native application that can efficiently scale and securely handle document processing in a distributed environment. •OCR Integration: Implement open-source OCR tools to extract text-based information, such as ID numbers and names, from scanned identification documents. •Ensure the application supports the use of uploaded documents and camera feed
Objectives | •Time Deadline 02/01/2025 •Scope : Fully functional and deployed application
Delivrables (Functional & Non functional requirements | •A fully functional cloud-native application capable of scanning identification documents. •Integration of open-source OCR tools for accurate text extraction. •Compatibility with various document formats, focusing on ID documents with possible integration of new documents type. •Implementation of a user-friendly web form test for seamless data insertion. Evaluation Criteria: •Accuracy of OCR text extraction. •Efficiency and scalability of the cloud-native application. •Robustness in handling different document formats. •User interface design and overall user experience.
Resources
Project Team | Roles | Platforms and frameworks
ELBOUZIDI HAMZA | Scrum master - Front end Developer | Azure Devops - Android Studio
MOUTASSIM BILAL | Teach lead - Tester | Jmeter - Junit - SonarQube
AZILAL AMINE | DevOps - Developer | Jenkins - kubernetes - docker
ABELLOUCH NOUSSAIR | OCR Model Developer | Python - Tesseract
ELQARI TARIK | Back end Developer | Spring boot
OUELD TIMIJJA AYA | Back end Developer | Spring boot
Milestones - Date | Dependencies | Constraints | Risks
Kickoff & Setup ¦ 05/12 - 07/12 | None | Team availability | Delays in Team availability
Initial Functional Features ¦ 07/12 - 13/12 | Kickoff, Setup | Scope clarity | Unclear requirements
MVP Development ¦ 13/12 - 20/12 | Initial Features | Team workload | Incomplete MVP features
Release 1 (MVP) ¦ 20/12 - 26/12 | MVP Development | Testing and review | Delays in testing or critical bugs
System Refinements ¦ 26/12 - 12/01 | Feedback from Release 1 | Scope adjustments | Bugs or issues with MVP
Final Presentation ¦ 16/01 | Final Release (MMP) | Stakeholder availability | Presentation issues or tech errors